## TODO
待办事项
状态统计 |  |  |  |  | 优先级统计 |  |  |  |  | 异常
任务数 | 按时完成 | 超时完成 | 其他 |  | 任务数 | 高 | 中 | 低 |  | 到期仍未完成
3 | 1 | 1 | 1 |  | 3 | 1 | 1 | 1 |  | 1
项目/任务 | 状态 | 优先级 | 难易度 | 指派给 | 指派日期 | 期望完成日期 | 实际完成日期 | 实际完成工作量 | 备注 | 剩余天数
Task Name 1 | 超时完成 | 高 | 简单/低价值 |  | 2015-03-16 | 2015-04-02 | 2015-04-05 | -16 |  | -
Task Name 2 | 按时完成 | 中 | 简单/高价值 |  | 2015-04-02 | 2015-04-05 | 2015-04-05 | -3 |  | -
Task Name 3 | 未完成 | 低 | 困难/高价值 |  | 2015-03-15 | 2015-03-20 |  | - |  | -11
| - | - | - |  |  |  |  | - |  | -
| - | - | - |  |  |  |  | - |  | -
| - | - | - |  |  |  |  | - |  | -
| - | - | - |  |  |  |  | - |  | -
| - | - | - |  |  |  |  | - |  | -
| - | - | - |  |  |  |  | - |  | -
| - | - | - |  |  |  |  | - |  | -
| - | - | - |  |  |  |  | - |  | -
| - | - | - |  |  |  |  | - |  | -
| - | - | - |  |  |  |  | - |  | -
| - | - | - |  |  |  |  | - |  | -
| - | - | - |  |  |  |  | - |  | -
| - | - | - |  |  |  |  | - |  | -
| - | - | - |  |  |  |  | - |  | -
| - | - | - |  |  |  |  | - |  | -
Formulas:
低 = IF([中]="","-",NETWORKDAYS([中],[优先级统计])-1)
异常 = IF([按时完成]="未完成",[高]-TODAY(),"-")
Note on D20: PICK is an acronym for: Possible (easy / low value) Implement (easy / high value) Challenge (hard / high value) Kill (hard / low value).

## Tracking
Project Tracking
公告 | Current Status |  |  |  | Projects |  | Deliverables |  |  |  | Cost / Hours
公告 | 状态 | 修改日期 | 优先级 | 版本 | 项目/任务 | 描述 | 交付物 | 交付日期 | % 完成 | 剩余天数 | 固定成本 | 预估工时 | 实际工时 | Billed Hrs
- | - |  | - |  | [ Project Title ] | [ Details ]
- | 完成 | 2011-11-07 | 低 | Phase1 | [ Sub Task ] | [ use comments for longer descriptions, but this field will also wrap ] | [ product xyz installation ] | 2012-09-01 | 100% | - | 0 |  |  | X
- | 审批通过 |  | 高 | Phase2 | [ Sub Task ] | [ this is an example of a task with multiple deliverables (rough and final drafts) ] | [ rough draft ] | 2014-04-10 | 50% | -355 | 2000 | 10 | 5
- | 审批通过 |  | - |  |  |  | [ final draft ] | 2015-04-05 | 0% | 5 | 0 | 10
- | - |  | - |  | Graphic Design | Create branding materials
- | - |  | 高 | Phase1 | Logo | [ short description ] | Illustrator file, .png, .gif |  |  |  | 0
- | - |  | 中 |  | Business Cards | [5 empty] | 0
- | - |  | 低 | Phase1 | Stationary | [5 empty] | 0
- | - |  | - | [7 empty] | 0
- | - |  | - |  | [ Project Title ] | [ Details ]
- | - |  | - | [7 empty] | 0
- | - |  | - | [7 empty] | 0
- | - |  | - | [7 empty] | 0
- | - |  | - | [7 empty] | 0
- | - |  | - |  | [ Project Title ] | [ Details ]
- | - |  | - | [7 empty] | 0
- | - |  | - | [7 empty] | 0
- | - |  | - | [7 empty] | 0
- | - |  | - | [7 empty] | 0
- | - |  | - |  | [ Project Title ] | [ Details ]
- | - |  | - | [7 empty] | 0
- | - |  | - | [7 empty] | 0
- | - |  | - | [7 empty] | 0
- | - |  | - | [7 empty] | 0

## 每周工作量统计（上周四~周三）
项目工作量统计 |  | 说明: 按照0.25 (15分钟)的比例增加工时.
|  |  | 加班工时 | 0
|  |  | 定期工时 | 640 |  | 总工时 （含假期） | 640
|  |  | 有效工时 | 640
开始日期 | 2015-03-19
结束日期 | 2015-03-25
| 姓名 | 职位 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 总工时 | 加班工时 | 定期工时
| 张雨舟 |  | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 40 |  | 40
| 杨正平 |  | 0 | 0 | 0 | 0 | 4 | 0 | 8 | 12 |  | 12
| 毛灯 |  | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 40 |  | 40
| 王世虎 |  | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 40 |  | 40
| 文良 |  | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 40 |  | 40
| 肖萍 |  | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 40 |  | 40
| 王志伟 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
| 田晓玲 |  | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 16 |  | 16
[10 empty] | 0 |  | 0
[10 empty] | 0 |  | 0
[10 empty] | 0 |  | 0
[10 empty] | 0 |  | 0
[10 empty] | 0 |  | 0
假期 | 2015-03-25 总工时: 0
病假 | 2015-03-25 总工时: 0
事假 | 2015-03-25 总工时: 0
合计 |  |  | 40 | 40 | 0 | 0 | 52 | 48 | 48 | 228 | 0 | 228
开始日期 | 2015-03-25 姓名: 2015-03-12
结束日期 | 2015-03-25 姓名: 2015-03-18
| 姓名 | 职位 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 总工时 | 加班工时 | 定期工时
| 张雨舟 |  | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 40 |  | 40
| 杨正平 |  | 8 | 8 | 0 | 0 | 0 | 4 | 8 | 28 |  | 28
| 毛灯 |  | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 40 |  | 40
| 王世虎 |  | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 40 |  | 40
| 文良 |  | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 40 |  | 40
| 肖萍 |  | 0 | 8 | 0 | 0 | 8 | 8 | 8 | 32 |  | 32
| 王志伟 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
[10 empty] | 0 |  | 0
[10 empty] | 0 |  | 0
[10 empty] | 0 |  | 0
[10 empty] | 0 |  | 0
[10 empty] | 0 |  | 0
[10 empty] | 0 |  | 0
假期 | 2015-03-18 总工时: 0
病假 | 2015-03-18 总工时: 0
事假 | 2015-03-18 总工时: 0
合计 |  |  | 40 | 48 | 0 | 0 | 40 | 44 | 48 | 220 | 0 | 220
开始日期 | 2015-03-18 姓名: 2015-03-05
结束日期 | 2015-03-18 姓名: 2015-03-11
| 姓名 | 职位 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 总工时 | 加班工时 | 定期工时
| 张雨舟 |  | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 40 |  | 40
| 杨正平 |  | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 24 |  | 24
| 毛灯 |  | 8 | 8 | 0 | 0 | 8 | 8 | 8 | 40 |  | 40
| 王世虎 |  | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 24 |  | 24
[10 empty] | 0 |  | 0
[10 empty] | 0 |  | 0
[10 empty] | 0 |  | 0
[10 empty] | 0 |  | 0
[10 empty] | 0 |  | 0
[10 empty] | 0 |  | 0
[10 empty] | 0 |  | 0
[10 empty] | 0 |  | 0
[10 empty] | 0 |  | 0
假期 | 2015-03-11 总工时: 0
病假 | 2015-03-11 总工时: 0
事假 | 2015-03-11 总工时: 0
合计 |  |  | 16 | 16 | 0 | 0 | 32 | 32 | 32 | 128 | 0 | 128
开始日期 | 2015-03-11 姓名: 2015-02-26
结束日期 | 2015-03-11 姓名: 2015-03-04
| 姓名 | 职位 | 四 | 五 | 六 | 日 | 一 | 二 | 三 | 总工时 | 加班工时 | 定期工时
| 张雨舟 |  | 0 | 0 | 6.5 | 8 | 8 | 8 | 8 | 38.5 |  | 38.5
| 杨正平 |  | 0 | 0 | 0 | 4 | 2 | 4 | 6 | 16 |  | 16
| 毛灯 |  | 0 | 0 | 0 | 0 | 0 | 1.5 | 8 | 9.5 |  | 9.5
[10 empty] | 0 |  | 0
[10 empty] | 0 |  | 0
[10 empty] | 0 |  | 0
[10 empty] | 0 |  | 0
[10 empty] | 0 |  | 0
[10 empty] | 0 |  | 0
[10 empty] | 0 |  | 0
[10 empty] | 0 |  | 0
[10 empty] | 0 |  | 0
[10 empty] | 0 |  | 0
假期 | 2015-03-04 总工时: 0
病假 | 2015-03-04 总工时: 0
事假 | 2015-03-04 总工时: 0
合计 |  |  | 0 | 0 | 6.5 | 12 | 10 | 13.5 | 22 | 64 | 0 | 64

## 工作量汇总
安保综合运营服务平台V1.0_工作量统计表
| 统计周期 |  | 项目经理 | 开发 | [7 empty] | 测试/质量/项目管理 | [5 empty] | 积分是否已分配 | 备注
总工作量 (人日） | 周工作量 （人日） | 统计时间 | AA | 毛灯 | 王世虎 | 文良 | 田晓玲 |  |  |  |  | 杨正平 | 王志伟 | 张雨舟 | 肖萍
24 | 24 | 2015.03.01-2015.03.11 | 0 | 7 | 3 | 0 | [5 empty] | 5 | 0 | 9 | 0 |  |  | 否
51.5 | 27.5 | 2015.03-12-2015.03-18 | 0 | 5 | 5 | 5 | [5 empty] | 3.5 | 0 | 5 | 4 |  |  | 否
80 | 28.5 | 2015.03-19-2015.03-25 | 0 | 5 | 5 | 5 | 2 |  |  |  |  | 1.5 | 0 | 5 | 5 |  |  | 否
否
否
否
否
否
否
合计 | 80 |  | 0 | 17 | 13 | 10 | 2 | 0 | 0 | 0 | 0 | 10 | 0 | 19 | 9 | 0 | 0
比重 |  |  | 0% | 21.25% | 16.25% | 12.5% | 2.5% | 0% | 0% | 0% | 0% | 12.5% | 0% | 23.75% | 11.25% | 0% | 0%
积分分配 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
目前人力费用（万元） |  | 3.2
立项预算
原计划人日 |  | XXXX人日
第1次变更后人日
第2次变更后人日
第3次变更后人日
类别 | 项目预算 | 实际总开支 | 序号 | 时间 | 金额 （元） | 事由
硬件及设备采购 | xx | 0
差旅 |  | 0
其他 |  | 0
Note on B17: 作者: 请输入总积分

## Ref
团队成员 | 优先级 | 状态 | 难易度 | 通知 | % 完成 | 版本
田志勇 | - | - | 简单/低价值 | - | - | -
杨正平 | 高 | 规划设计 | 简单/高价值 | RAR | 10% | Phase1
王志伟 | 中 | 待审批 | 困难/高价值 | FYI | 20% | Phase2
张雨舟 | 低 | 审批通过 | 困难/低价值 | NTD | 30% | Phase3
王世虎 |  | 进行中 |  |  | 40% | Phase4
文良 |  | 待审核 |  |  | 50%
毛灯 |  | 暂停 |  |  | 60%
肖萍 |  | 完成 |  |  | 70%
田晓玲 |  |  |  |  | 80%
90%
100%